## triz de Gerenciamento de Riscos
MATRIZ DE GERENCIAMENTO DE RISCOS
NOME | NS Clothing new Website |  |  |  | OBJETIVO | Mitigate potential risks to project goal achievement
REF/ID | PRÉ-MITIGAÇÃO |  |  |  | DEPARTAMENTO / LOCALIZAÇÃO | ATENUAÇÕES / AVISOS / REMÉDIOS | PÓS-MITIGAÇÃO |  |  |  | CHAVE DE GRAVIDADE DE RISCO | CHAVE DE PROBABILIDADE DE RISCO | CHAVE DE NÍVEL DE RISCO | ACEITÁVEL PARA PROSSEGUIR? CHAVE
| RISCO | GRAVIDADE DO RISCO | PROBABILIDADE DE RISCO | NÍVEL DE RISCO |  |  | GRAVIDADE DO RISCO | PROBABILIDADE DE RISCO | NÍVEL DE RISCO | ACEITÁVEL PARA PROSSEGUIR?
1 | Vulnerabilities in the site's security that could lead to data breaches, unauthorized access, or financial loss. | INTOLERÁVEL | POSSÍVEL | EXTREMO | Security Concerns | Implement robust security measures, use secure payment gateways, encrypt sensitive data, and conduct regular security audits. | INTOLERÁVEL | IMPROVÁVEL | EXTREMO | NÃO | ACEITÁVEL | IMPROVÁVEL | BAIXO | SIM
2 | Payment gateway integration challenges that result in transaction failures or security issues. | INTOLERÁVEL | POSSÍVEL | EXTREMO | Payment gateway integration | Thoroughly test payment gateway integrations, work closely with reputable payment service providers, and comply with PCI DSS standards. | INTOLERÁVEL | IMPROVÁVEL | EXTREMO | NÃO | TOLERÁVEL | POSSÍVEL | MÉDIA | NÃO
3 | Inability of the site to handle increased traffic and transactions during peak periods, resulting in slow performance or crashes. | INTOLERÁVEL | PROVÁVEL | EXTREMO | Scalability Challenges | Perform load testing to ensure scalability, use content delivery networks (CDNs), and choose a hosting infrastructure that can handle traffic spikes. | INTOLERÁVEL | IMPROVÁVEL | EXTREMO | NÃO | INDESEJÁVEL | PROVÁVEL | ALTO
4 | Inconsistencies in site rendering and functionality across browsers and devices. | INDESEJÁVEL | POSSÍVEL | ALTO | Compatibility and cross-browser | Conduct extensive cross-browser and cross-device testing, adhere to Web standards, and use responsive design techniques. | INDESEJÁVEL | IMPROVÁVEL | MÉDIA | SIM | INTOLERÁVEL |  | EXTREMO
5 | Changes in project requirements or incomplete understanding of customer needs can lead to scope creep and delays. | INDESEJÁVEL | POSSÍVEL | ALTO | Incomplete or changing requirements | Clearly define project requirements, maintain constant communication with stakeholders, and use agile development methodologies to adapt to changes. | INDESEJÁVEL | IMPROVÁVEL | MÉDIA | SIM
6 | Problems integrating third-party APIs, inventory management systems, or other external services. | INDESEJÁVEL | POSSÍVEL | ALTO | Integration Challenges | Prioritize API compatibility, thoroughly test integrations, and choose reputable and well-documented APIs. | INDESEJÁVEL | IMPROVÁVEL | MÉDIA | SIM
7 | Poor user experience, confusing navigation, or usability issues that result in high bounce rates. | INTOLERÁVEL | POSSÍVEL | EXTREMO | User experience (UX) and usability | Conduct usability testing, gather user feedback, and prioritize intuitive design and navigation. | INTOLERÁVEL | IMPROVÁVEL | EXTREMO | NÃO
8 | Challenges in migrating existing data to the new eCommerce platform without data loss or corruption. | INDESEJÁVEL | POSSÍVEL | ALTO | Data migration | Carefully plan and execute data migration, validate data integrity, and perform thorough post-migration testing. | INDESEJÁVEL | IMPROVÁVEL | MÉDIA | SIM
9 | Failure to comply with regulatory requirements, such as privacy laws or accessibility standards. | INTOLERÁVEL | IMPROVÁVEL | EXTREMO | Legal and compliance | Stay informed about relevant regulations, implement necessary compliance measures, and seek legal advice when necessary. | INTOLERÁVEL | IMPROVÁVEL | EXTREMO | NÃO
10 | Rapid changes in technology that make certain components or technologies used in the Web site obsolete. | TOLERÁVEL | POSSÍVEL | MÉDIA | Technology obsolescence | Stay abreast of technology advancements, choose scalable and adaptable technologies. | TOLERÁVEL | IMPROVÁVEL | MÉDIA | SIM
CLIQUE AQUI PARA CRIAR NO SMARTSHEET