## Estimative
TASK | COST | TIME | PEOPLE
Project Planning and Analysis. | $6,ooo | 30 days | 1 Business Analyst
Domain and Hosting: define and contract. | $10,000 | 5 days | 1 Business Analyst 1 Finance Manager
Platform and Technology selection: define, contract, and install. | $100,000 | 5 days | 1 Business Analyst 1 Finance Manager 1 DevOps Engineer
Website Design: personas, layout, brand, prototyping. | $12,000 | 60 days from developing to approval | 2 UX Analysts 1 UI Analyst/Dev
Front-End Development: WordPress, WooCommerce | $60,000 | 90 days | 2 Fullstack (UI) developers WordPress, WooCommerce
Back-End Development: database structures, business logic, integrations with legacy systems, WooCommerce: WordPress plugin that adds e-commerce functionality to WordPress websites. | $60,000 | 90 days | 2 SQL Server DBA / Back-End developers: SQL Server
Shopping Cart, Checkout, and Payment: integration with payment platforms. | $10,000 | 15 days | 1 Back-End developer
Content Creation: website content (text, images, videos). | $30,000 | 60 days | 2 editors 1 approver
AI and Machine Learning for Product Recommendations: implement AI and machine learning algorithms to analyze customer behavior and preferences. | $30,000 | 30 days | 1 Data Scientist
Enhanced Search Functionality: with Elasticsearch | $30,000 | 30 days | 1 Elasticsearch Specialist
Monitoring & Analytics: implement analytics tools to gather data on user behavior, sales metrics, and website performance to support decision-making. | $20,000 | 30 days | 1 Data Analyst
Product Management: images, descriptions, pricing, categorization, tagging, and inventory. | $8,000 | 30 days | 1 from Operations and Master Data
Compliance and Regulations: tax compliance, auditing, regulations. | $8,000 | 15 days | 1 from Accounting
User Authentication and Authorization: Azure Active Directory. | $10,000 | 5 days | 1 Back-End developer 1 DevOps Engineer
Security & Privacy: Implement SSL encryption for secure data transmission. | $10,000 | 15 days | 1 Back-End developer
Quality Assurance: test functionality, usability, performance, and security. Perform cross-browser and cross-device testing. | $30,000 | 90 days days | 1 Quality Assurance Specialist
Training and Documentation: training for content creators and administrators on how to update and manage the website. | 20,000 | 60 days | 2 Product Owners
Launch: announce the launch of the website to stakeholders and users. | $10,000 | 30 days | 1 from Marketing Department
Marketing and Promotion: utilize social media, email, and other channels for promotion. | $30,000 | 30 days before lauch | 2 from Marketing Department
Analytics Setup: set up analytics tools to track website performance and user behavior (Google Analytics). | $5,000 | 5 days | 1 Full-Stack Developer
Maintenance: optimize website speed, SEO, and user experience based on analytics insights. | $8,000 | Monthly (routine) | 1 from Marketing: SEO, Feedbacks, Interations

## Prioritization
TASK | PRIORITY
Project Planning and Analysis. | MUST HAVE
Domain and Hosting: define and contract. | SHOULD HAVE
Platform and Technology selection: define, contract, and install. | MUST HAVE
Website Design: personas, layout, brand, prototyping. | SHOULD HAVE
Front-End Development: WordPress, WooCommerce | MUST HAVE
Back-End Development: database structures, business logic, integrations with legacy systems, WooCommerce: WordPress plugin that adds e-commerce functionality to WordPress websites. | MUST HAVE
Shopping Cart, Checkout, and Payment: integration with payment platforms. | MUST HAVE
Content Creation: website content (text, images, videos). | MUST HAVE
AI and Machine Learning for Product Recommendations: implement AI and machine learning algorithms to analyze customer behavior and preferences. | MUST HAVE
Enhanced Search Functionality: with Elasticsearch | SHOULD HAVE
Monitoring & Analytics: implement analytics tools to gather data on user behavior, sales metrics, and website performance to support decision-making. | MUST HAVE
Product Management: images, descriptions, pricing, categorization, tagging, and inventory. | MUST HAVE
Compliance and Regulations: tax compliance, auditing, regulations. | MUST HAVE
User Authentication and Authorization: Azure Active Directory. | MUST HAVE
Security & Privacy: Implement SSL encryption for secure data transmission. | SHOULD HAVE
Quality Assurance: test functionality, usability, performance, and security. Perform cross-browser and cross-device testing. | SHOULD HAVE
Training and Documentation: training for content creators and administrators on how to update and manage the website. | SHOULD HAVE
Launch: announce the launch of the website to stakeholders and users. | SHOULD HAVE
Marketing and Promotion: utilize social media, email, and other channels for promotion. | COULD HAVE
Analytics Setup: set up analytics tools to track website performance and user behavior (Google Analytics). | MUST HAVE
Maintenance: optimize website speed, SEO, and user experience based on analytics insights. | COULD HAVE

## Communication
Description | Frequency | Channel | Audience | Owner
Project Status update | weekly | MS-Project | All internal stakeholders and project members | Project Manager
Virtual project team meetings | monthly | MS-Teams | All project members, stakeholders (optional) | Project Manager
External stakeholders updates | as needed | MS-Teams | Project manager and project stackholders | Project Manager e Project Sponsor
Milestone and deliverable updates | as needed | MS-Project Intranet | Project members | Project members
Project check-ins | daily | MS-Teams | Project members | Project members
Announcements | as needed | Intranet | All company | Project members